## Dashboard
thrift it! — Vintage Clothing Marketplace — Task & Timeline Tracker
Last updated: 2026-10-03
📊 KPI Summary
Total Tasks |  | Done |  | In Progress | To Do
47 |  | 26 |  | 1 | 11
Blocked |  | Backlog |  | % Complete | Active Effort (h)
1 |  | 8 |  | 55.3% | 81
Status Distribution
Status | Count | % | Effort (h) | Module
Done | 26 | 55.3% | 69 | BE, BUG, DB, DOC, FE, QA
In Progress | 1 | 2.1% | 12 | BE
To Do | 11 | 23.4% | 64 | BE, CLEAN, FE, QA
Blocked | 1 | 2.1% | 16 | QA
Backlog | 8 | 17.0% | 152 | BE, DB, FE, INFRA
Effort per Module
Module | Tasks | Total Effort (h) | Done Effort (h) | % Complete
BE | 13 | 110 | 18 | 16.4%
BUG | 3 | 2.5 | 2.5 | 100.0%
CLEAN | 3 | 6 | 0 | 0.0%
DB | 3 | 9 | 5 | 55.6%
DOC | 3 | 6 | 6 | 100.0%
FE | 15 | 140 | 36 | 25.7%
INFRA | 2 | 20 | 0 | 0.0%
QA | 5 | 19.5 | 1.5 | 7.7%

## All Tasks
ID | Title | Module | Priority | Owner | Status | Effort (h) | Sprint | Start | End | Notes
FE-101 | AddressBook component + useAddressCatalog hook | FE | P0 | @frontend-lead | Done | 8 | S7 | 2026-09-26 | 2026-09-27 | docs/USER_MANUAL.md §3.9
FE-102 | CAS API — 2-tier administrative hierarchy | FE | P0 | @frontend-dev | Done | 6 | S7 | 2026-09-27 | 2026-09-28 | Bỏ Quận/Huyện
FE-103 | PaymentScreen auto-fill từ AddressBook | FE | P0 | @frontend-dev | Done | 4 | S7 | 2026-09-28 | 2026-09-28 | AddressPickerModal
FE-104 | AddressBookTab (Buyer) — CRUD đầy đủ | FE | P0 | @frontend-dev | Done | 5 | S7 | 2026-09-28 | 2026-09-29
FE-105 | WarehouseTab (Seller) — pickup address | FE | P0 | @frontend-dev | Done | 5 | S7 | 2026-09-29 | 2026-09-30
FE-106 | LetterAvatar + PlaceholderImage thay Unsplash | FE | P1 | @frontend-dev | Done | 3 | S7 | 2026-09-30 | 2026-09-30
FE-107 | Auto-fill pickup từ warehouse trong shipment dialog | FE | P1 | @frontend-dev | Done | 2 | S7 | 2026-10-01 | 2026-10-01
FE-108 | Xóa legacy placeholder Quận/Huyện | FE | P2 | @frontend-dev | Done | 1 | S7 | 2026-10-02 | 2026-10-02
FE-109 | Loading & error states cho AddressBook | FE | P1 | @frontend-dev | Done | 2 | S7 | 2026-10-01 | 2026-10-01 | Catalog fail → free-text fallback
BE-201 | addressService.ts — proxy CAS Address Kit | BE | P0 | @backend-lead | Done | 6 | S7 | 2026-09-26 | 2026-09-27 | 24h in-memory cache
BE-202 | addressController + routes | BE | P0 | @backend-dev | Done | 3 | S7 | 2026-09-27 | 2026-09-27 | 3 endpoints: provinces, communes
BE-203 | Snapshot địa chỉ vào Order | BE | P0 | @backend-dev | Done | 4 | S7 | 2026-09-28 | 2026-09-29 | shippingProvinceId, ward
BE-204 | test:address (16/16 PASS) | BE | P1 | @backend-dev | Done | 3 | S7 | 2026-10-01 | 2026-10-01
BE-205 | 5s timeout cho CAS requests (AbortController) | BE | P1 | @backend-dev | Done | 1 | S7 | 2026-09-30 | 2026-09-30
BE-206 | Validate effectiveDate (latest¦YYYY-MM-DD) | BE | P2 | @backend-dev | Done | 1 | S7 | 2026-10-02 | 2026-10-02
DB-301 | Migration: address snapshot fields vào Order | DB | P0 | @backend-lead | Done | 3 | S7 | 2026-09-28 | 2026-09-28
DB-302 | Update mapOrder adapter | DB | P0 | @backend-dev | Done | 2 | S7 | 2026-09-29 | 2026-09-29
DB-303 | Backfill address snapshots cho orders cũ | DB | P3 | @backend-dev | Backlog | 4 | S8 | 2026-10-06 | 2026-10-07 | Cần script riêng
QA-401 | Backend build pass (npm run build) | QA | P0 | @qa | Done | 0.5 | S7 | 2026-10-03 | 2026-10-03 | Exit 0
QA-402 | Backend tests pass (errorContract) | QA | P0 | @qa | Done | 0.5 | S7 | 2026-10-03 | 2026-10-03 | 38/38 PASS
QA-403 | Frontend build pass (vite) | QA | P0 | @qa | Done | 0.5 | S7 | 2026-10-03 | 2026-10-03 | Bundle 448 KB JS / 122 KB CSS
QA-404 | Live test /api/users/me/addresses | QA | P0 | @qa | To Do | 2 | S7 | 2026-10-03 | 2026-10-04 | Cần MongoDB live connection
DOC-501 | Update AI_CONTEXT.md | DOC | P0 | @frontend-lead | Done | 1 | S7 | 2026-10-03 | 2026-10-03 | Updated 2026-10-03
DOC-502 | USER_MANUAL.md (1083 dòng) | DOC | P1 | @doc-team | Done | 3 | S7 | 2026-10-02 | 2026-10-02
DOC-503 | Slides .pptx (28 slides) | DOC | P2 | @doc-team | Done | 2 | S7 | 2026-10-03 | 2026-10-03 | 16:9 widescreen
BUG-001 | ORDER_BUYER_NOT_PARTICIPANT — buyer không transition DELIVERED | BUG | P0 | @backend-lead | Done | 1 | S6 | 2026-10-01 | 2026-10-01 | Fix 2026-10-01
BUG-002 | Avatar chỉ update seller, không sync User | BUG | P0 | @backend-dev | Done | 1 | S6 | 2026-10-01 | 2026-10-01 | Fix 2026-10-01
BUG-003 | Seller không set DELIVERING/DELIVERED trực tiếp | BUG | P1 | @backend-dev | Done | 0.5 | S6 | 2026-10-01 | 2026-10-01 | Fix 2026-10-01
BE-301 | Ledger.ts — double-entry accounting model | BE | P0 | @backend-lead | In Progress | 12 | S8 | 2026-10-04 | 2026-10-06 | 4 accounts, idempotency
BE-302 | PlatformFeeConfig.ts — flexible commission rates | BE | P0 | @backend-lead | To Do | 8 | S8 | 2026-10-06 | 2026-10-07 | Theo thời điểm đặt hàng
BE-303 | Refactor getAdminStats dùng Ledger | BE | P0 | @backend-dev | To Do | 6 | S8 | 2026-10-08 | 2026-10-08 | Chống drift
BE-304 | Migration: backfill Ledger cho orders COMPLETED | BE | P0 | @backend-dev | To Do | 6 | S8 | 2026-10-09 | 2026-10-09 | Reconcile với Order.platformFee
BE-305 | Admin endpoint cập nhật rate (audit trail) | BE | P1 | @backend-dev | To Do | 4 | S8 | 2026-10-09 | 2026-10-09
CLEAN-401 | Xóa /api/auth/cart/merge (deprecated) | CLEAN | P2 | @backend-dev | To Do | 1 | S8 | 2026-10-08 | 2026-10-08
CLEAN-402 | Xóa legacy /api/admin/users/:id/{approve,reject}-seller | CLEAN | P2 | @backend-dev | To Do | 1 | S8 | 2026-10-08 | 2026-10-08
CLEAN-403 | Cleanup Unsplash fallbacks toàn bộ FE | CLEAN | P3 | @frontend-dev | To Do | 4 | S8 | 2026-10-09 | 2026-10-09
FE-301 | UI thanh toán online (card / ví điện tử) | FE | P1 | @frontend-dev | To Do | 12 | S8 | 2026-10-07 | 2026-10-08 | Hiện chỉ có COD
FE-302 | Stripe / VNPay integration | FE | P1 | @frontend-dev | To Do | 16 | S8 | 2026-10-09 | 2026-10-10 | Phụ thuộc backend webhook
FE-303 | Hiển thị platform fee cho seller khi đặt giá | FE | P2 | @frontend-dev | To Do | 4 | S8 | 2026-10-10 | 2026-10-10
QA-501 | E2E test toàn flow mua hàng (Playwright) | QA | P1 | @qa | Blocked | 16 | S8 | 2026-10-08 | 2026-10-10 | Cần staging env
FE-X01 | Chat Buyer ↔ Seller real-time (WebSocket) | FE | P1 | TBD | Backlog | 40 | Q4 | 2026-11-01 | 2026-11-15 | Hiện là preview/mock
FE-X02 | Đánh giá nâng cao (ảnh review, reply) | FE | P2 | TBD | Backlog | 24 | Q4 | 2026-11-15 | 2026-11-30
FE-X03 | Wishlist / Favorites page riêng | FE | P2 | TBD | Backlog | 8 | Q4 | 2026-10-15 | 2026-10-17
BE-X01 | Seller analytics dashboard | BE | P2 | TBD | Backlog | 16 | Q4 | 2026-11-01 | 2026-11-05
BE-X02 | Recommendation engine (collaborative filtering) | BE | P3 | TBD | Backlog | 40 | Q4 | 2026-11-15 | 2026-12-05
INFRA-X01 | CI/CD pipeline (GitHub Actions) | INFRA | P1 | @devops | Backlog | 12 | Q4 | 2026-11-01 | 2026-11-03 | Hiện manual deploy Render
INFRA-X02 | Monitoring & alerts (Sentry, UptimeRobot) | INFRA | P2 | @devops | Backlog | 8 | Q4 | 2026-11-05 | 2026-11-07

## Gantt
ID | Title | Start | End | Days | 09-26 | 09-27 | 09-28 | 09-29 | 09-30 | 10-01 | 10-02 | 10-03 | 10-04 | 10-05 | 10-06 | 10-07 | 10-08 | 10-09 | 10-10 | 10-11 | 10-12 | 10-13 | 10-14 | 10-15 | 10-16 | 10-17 | 10-18 | 10-19 | 10-20 | 10-21 | 10-22 | 10-23 | 10-24 | 10-25 | 10-26 | 10-27 | 10-28 | 10-29 | 10-30 | 10-31 | 11-01 | 11-02 | 11-03 | 11-04 | 11-05 | 11-06 | 11-07 | 11-08 | 11-09 | 11-10 | 11-11 | 11-12 | 11-13 | 11-14 | 11-15 | 11-16 | 11-17 | 11-18 | 11-19 | 11-20 | 11-21 | 11-22 | 11-23 | 11-24 | 11-25 | 11-26 | 11-27 | 11-28 | 11-29 | 11-30 | 12-01 | 12-02 | 12-03 | 12-04 | 12-05
FE-101 | AddressBook component + useAddressCatalog hook | 2026-09-26 | 2026-09-27 | 2
FE-102 | CAS API — 2-tier administrative hierarchy | 2026-09-27 | 2026-09-28 | 2
FE-103 | PaymentScreen auto-fill từ AddressBook | 2026-09-28 | 2026-09-28 | 1
FE-104 | AddressBookTab (Buyer) — CRUD đầy đủ | 2026-09-28 | 2026-09-29 | 2
FE-105 | WarehouseTab (Seller) — pickup address | 2026-09-29 | 2026-09-30 | 2
FE-106 | LetterAvatar + PlaceholderImage thay Unsplash | 2026-09-30 | 2026-09-30 | 1
FE-107 | Auto-fill pickup từ warehouse trong shipment dialog | 2026-10-01 | 2026-10-01 | 1
FE-108 | Xóa legacy placeholder Quận/Huyện | 2026-10-02 | 2026-10-02 | 1
FE-109 | Loading & error states cho AddressBook | 2026-10-01 | 2026-10-01 | 1
BE-201 | addressService.ts — proxy CAS Address Kit | 2026-09-26 | 2026-09-27 | 2
BE-202 | addressController + routes | 2026-09-27 | 2026-09-27 | 1
BE-203 | Snapshot địa chỉ vào Order | 2026-09-28 | 2026-09-29 | 2
BE-204 | test:address (16/16 PASS) | 2026-10-01 | 2026-10-01 | 1
BE-205 | 5s timeout cho CAS requests (AbortController) | 2026-09-30 | 2026-09-30 | 1
BE-206 | Validate effectiveDate (latest¦YYYY-MM-DD) | 2026-10-02 | 2026-10-02 | 1
DB-301 | Migration: address snapshot fields vào Order | 2026-09-28 | 2026-09-28 | 1
DB-302 | Update mapOrder adapter | 2026-09-29 | 2026-09-29 | 1
DB-303 | Backfill address snapshots cho orders cũ | 2026-10-06 | 2026-10-07 | 2
QA-401 | Backend build pass (npm run build) | 2026-10-03 | 2026-10-03 | 1
QA-402 | Backend tests pass (errorContract) | 2026-10-03 | 2026-10-03 | 1
QA-403 | Frontend build pass (vite) | 2026-10-03 | 2026-10-03 | 1
QA-404 | Live test /api/users/me/addresses | 2026-10-03 | 2026-10-04 | 2
DOC-501 | Update AI_CONTEXT.md | 2026-10-03 | 2026-10-03 | 1
DOC-502 | USER_MANUAL.md (1083 dòng) | 2026-10-02 | 2026-10-02 | 1
DOC-503 | Slides .pptx (28 slides) | 2026-10-03 | 2026-10-03 | 1
BUG-001 | ORDER_BUYER_NOT_PARTICIPANT — buyer không transition DELIVERED | 2026-10-01 | 2026-10-01 | 1
BUG-002 | Avatar chỉ update seller, không sync User | 2026-10-01 | 2026-10-01 | 1
BUG-003 | Seller không set DELIVERING/DELIVERED trực tiếp | 2026-10-01 | 2026-10-01 | 1
BE-301 | Ledger.ts — double-entry accounting model | 2026-10-04 | 2026-10-06 | 3
BE-302 | PlatformFeeConfig.ts — flexible commission rates | 2026-10-06 | 2026-10-07 | 2
BE-303 | Refactor getAdminStats dùng Ledger | 2026-10-08 | 2026-10-08 | 1
BE-304 | Migration: backfill Ledger cho orders COMPLETED | 2026-10-09 | 2026-10-09 | 1
BE-305 | Admin endpoint cập nhật rate (audit trail) | 2026-10-09 | 2026-10-09 | 1
CLEAN-401 | Xóa /api/auth/cart/merge (deprecated) | 2026-10-08 | 2026-10-08 | 1
CLEAN-402 | Xóa legacy /api/admin/users/:id/{approve,reject}-seller | 2026-10-08 | 2026-10-08 | 1
CLEAN-403 | Cleanup Unsplash fallbacks toàn bộ FE | 2026-10-09 | 2026-10-09 | 1
FE-301 | UI thanh toán online (card / ví điện tử) | 2026-10-07 | 2026-10-08 | 2
FE-302 | Stripe / VNPay integration | 2026-10-09 | 2026-10-10 | 2
FE-303 | Hiển thị platform fee cho seller khi đặt giá | 2026-10-10 | 2026-10-10 | 1
QA-501 | E2E test toàn flow mua hàng (Playwright) | 2026-10-08 | 2026-10-10 | 3
FE-X01 | Chat Buyer ↔ Seller real-time (WebSocket) | 2026-11-01 | 2026-11-15 | 15
FE-X02 | Đánh giá nâng cao (ảnh review, reply) | 2026-11-15 | 2026-11-30 | 16
FE-X03 | Wishlist / Favorites page riêng | 2026-10-15 | 2026-10-17 | 3
BE-X01 | Seller analytics dashboard | 2026-11-01 | 2026-11-05 | 5
BE-X02 | Recommendation engine (collaborative filtering) | 2026-11-15 | 2026-12-05 | 21
INFRA-X01 | CI/CD pipeline (GitHub Actions) | 2026-11-01 | 2026-11-03 | 3
INFRA-X02 | Monitoring & alerts (Sentry, UptimeRobot) | 2026-11-05 | 2026-11-07 | 3

## Risks
ID | Risk | Impact | Probability | Mitigation | Owner
R-01 | Ledger chưa xong → platformProfit có thể drift | High | Medium | Implement S8 ngay tuần đầu | @backend-lead
R-02 | CAS API thay đổi schema → break address picker | Medium | Low | Fallback free-text + cache 24h | @backend-dev
R-03 | Render.com free tier exhausted → downtime | Medium | Medium | Monitor usage, có plan upgrade | @devops
R-04 | Thiếu E2E tests → regression bugs khi refactor | High | Medium | Setup Playwright + staging S8 | @qa
R-05 | Mobile app chưa đồng bộ với backend | Medium | Low | Sync API contract trước mỗi release | @mobile-lead

## Team Workload
Owner | Active Tasks | Total Effort (h) | Done Effort (h) | In Progress Effort (h) | To Do Effort (h)
@backend-dev | 13 | 37.5 | 15.5 | 0 | 18
@backend-lead | 5 | 30 | 10 | 12 | 8
@devops | 0 | 20 | 0 | 0 | 0
@doc-team | 2 | 5 | 5 | 0 | 0
@frontend-dev | 12 | 64 | 28 | 0 | 36
@frontend-lead | 2 | 9 | 9 | 0 | 0
@qa | 5 | 19.5 | 1.5 | 0 | 2

## Milestones
Date | Milestone | Status | Owner
2026-07-15 | MVP — Auth & Product CRUD | Done | @backend-lead
2026-08-01 | Seller Application Flow | Done | @backend-dev
2026-08-15 | Cart + Checkout (COD) | Done | @fullstack
2026-09-01 | Shipment GHTK Integration | Done | @backend-dev
2026-09-15 | Reviews + Admin Panel | Done | @fullstack
2026-10-03 | Address Book + CAS | Done | @frontend-lead
2026-10-10 | Ledger + Payment | In Progress | @backend-lead
2026-10-24 | Online Payment MVP | Planned | @fullstack
2026-11-15 | Beta Launch (200 users) | Planned | @pm
2026-12-01 | Public Launch | Planned | @all